## WBS & GanttChart
Equipping Urban Greenhouse with Rainwater Harvesting System and PV
Display Week : | 1
Project Start Date : | 2024-01-01 | [8 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
Project Manager: | Sayed Mohammad Sajjadi | [8 empty] | 2024-01-01 | [6 empty] | 2024-01-08 | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29
[10 empty] | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04
DELIVERABLES | TASKS | WBS | PREDECESSOR | START | END | DAYS | Cost | Resource Allocation | % DONE | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Phase 1 : Research and Planning
Conduct site assessment | Take Detailed Measurements of the Greenhouse Environment | 1.1.1 | Start | 2024-01-01 | 2024-01-01 | 1 | 10 | SE | 100%
| Evaluate Suitable Space for Equipment Installation | 1.1.2 | 1.1.1 | 2024-01-01 | 2024-01-01 | 1 | 10 | SE | 100%
Determine rainwater harvesting system requirements | Assess water needs | 1.2.1 | 1.1.1 | 2024-01-02 | 2024-01-02 | 1 | 50 | SE | 100%
| Analyze rainfall patterns | 1.2.2 | 1.1.1 | 2024-01-02 | 2024-01-02 | 1 | 50 | SE | 100%
| Consider storage capacity | 1.2.3 | 1.2.1 , 1.2.2 | 2024-01-02 | 2024-01-02 | 1 | 50 | SE | 100%
| Evaluate filtration requirements | 1.2.4 | 1.2.3 | 2024-01-02 | 2024-01-02 | 1 | 50 | SE | 100%
| Design and specify components | 1.2.5 | 1.2.4 | 2024-01-02 | 2024-01-02 | 1 | 50 | SE | 100%
Determine PV system requirements | Calculate energy needs | 1.3.1 | 1.1.1 | 2024-01-03 | 2024-01-04 | 2 | 40 | SE | 100%
| Evaluate solar radiation | 1.3.2 | 1.1.1 | 2024-01-03 | 2024-01-04 | 2 | 40 | SE | 100%
| Determine panel size and quantity | 1.3.3 | 1.3.1 , 1.3.2 | 2024-01-03 | 2024-01-04 | 2 | 25 | SE | 100%
| Design and specify components | 1.3.4 | 1.3.3 | 2024-01-03 | 2024-01-04 | 2 | 25 | SE | 100%
Develop system design | Integrate rainwater harvesting and PV systems | 1.4.1 | 1.2.5 , 1.3.4 | 2024-01-05 | 2024-01-05 | 1 | 50 | SE | 100%
| Create detailed drawings and specifications | 1.4.2 | 1.4.1 | 2024-01-05 | 2024-01-05 | 1 | 50 | SE | 100%
Phase 2 : Procurement
Identify and select suppliers | Identify and select supplier for PV and its required components | 2.1.1 | 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 5 | PM | 100%
| Identify and select suppliers for rainwater harvesting system components | 2.1.2 | 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 10 | PM | 100%
Prepare purchase orders | Purchase PV and required components | 2.2.1 | 2.1.1, 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 300 | PM | 100%
| Purchase Storage tanks | 2.2.2 | 2.1.2, 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 3000 | PM | 100%
| Purchase sediment filter | 2.2.3 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 650 | PM | 100%
| Purchase ultraviolet (UV) filter | 2.2.4 | 2.1.2, 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 1300 | PM | 100%
| Purchase submersible pump | 2.2.5 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 500 | PM | 100%
| Purchase control panel | 2.2.6 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 400 | PM | 100%
| Purchase distribution pipes | 2.2.7 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 500 | PM | 100%
Coordinate delivery schedules | Coordinate delivery schedules | 2.3.1 | 2.2.1 , 2.2.2 , 2.2.3 , 2.2.4 , 2.2.5 , 2.2.6 , 2.2.7 | 2024-01-08 | 2024-01-10 | 3 | 140 | PM | 100%
Phase 3 : Installation
Site Preparation | Clearing and grading the ground for tank placement | 3.1.1 | 2.2.2 | 2024-01-09 | 2024-01-09 | 1 | 400 | RHT (2) | 100%
| Excavation for tank installation | 3.1.2 | 2.2.2 | 2024-01-10 | 2024-01-10 | 1 | 800 | RHT (2) | 100%
Tank Installation | Delivery and installation of rainwater storage tanks | 3.2.1 | 2.3.1 | 2024-01-11 | 2024-01-11 | 1 | 100 | RHT (2) | 100%
| Connection of pipes to the tank | 3.2.2 | 2.3.1 , 3.2.1 | 2024-01-12 | 2024-01-12 | 1 | 120 | RHT (2) | 100%
Install Filtration System | Installation of sediment filter | 3.3.1 | 3.2.1 , 2.3.1 | 2024-01-15 | 2024-01-15 | 1 | 200 | RHT (1) | 100%
| Installation of ultraviolet (UV) filter | 3.3.2 | 3.2.1 , 2.3.1 | 2024-01-15 | 2024-01-15 | 1 | 200 | RHT (1) | 100%
Install Pumping System | Installation of submersible pump | 3.4.1 | 3.2.1 , 2.3.1 | 2024-01-16 | 2024-01-16 | 1 | 200 | RHT (1) | 100%
| Installation of control panel | 3.4.2 | 3.4.1 , 2.3.1 | 2024-01-16 | 2024-01-16 | 1 | 120 | RHT (1) | 100%
Install Distribution System | Installation of collection and distribution pipes | 3.5.1 | 3.4.1 , 2.3.1 | 2024-01-17 | 2024-01-17 | 1 | 200 | RHT (1) | 100%
| Installation of irrigation system | 3.5.2 | 3.4.1 , 2.3.1 | 2024-01-17 | 2024-01-17 | 1 | 200 | RHT (1) | 100%
Install PV System | Install PV modules and mounting structures | 3.6.1 | 2.3.1 | 2024-01-11 | 2024-01-11 | 1 | 75 | ET (1) | 100%
| Connect PV system to electrical infrastructure | 3.6.2 | 3.6.1 | 2024-01-12 | 2024-01-12 | 1 | 50 | ET (1) | 100%
Phase 4 : Testing and Commissioning
Perform necessary tests | Perform functionality tests on rainwater harvesting system and optimize it | 4.1.1 | 3.5.2 | 2024-01-18 | 2024-01-18 | 1 | 20 | PM | 100%
| Perform electrical tests on the PV system and optimize it | 4.1.2 | 3.6.2 | 2024-01-18 | 2024-01-18 | 1 | 15 | PM | 100%
Obtain necessary certifications and approvals | Register for the Conto Termico 2.0 (CT2) program | 4.2.1 | 2.2.1 | 2024-01-09 | 2024-01-18 | 10 | 10 | PM | 100%
| Obtain electrical and structural permits | 4.2.2 | 2.2.1 | 2024-01-09 | 2024-01-18 | 10 | 10 | PM | 70%
| Obtain certifications for PV components | 4.2.3 | 2.2.1 | 2024-01-09 | 2024-01-16 | 8 | 10 | PM | 100%
| Obtain certifications for rainwater harvesting system components | 4.2.4 | 1.4.2 | 2024-01-09 | 2024-01-12 | 4 | 10 | PM | 100%
| Obtain authorization for rainwater discharge | 4.2.5 | 1.4.2 | 2024-01-09 | 2024-01-23 | 15 | 10 | PM | 50%
Phase 5 : Documentation
Create user manuals | Create user manuals for rainwater harvesting system | 5.1.1 | 4.1.1 | 2024-01-19 | 2024-01-19 | 1 | 50 | PM | 10%
| Create user manuals for PV system | 5.1.2 | 4.1.2 | 2024-01-22 | 2024-01-22 | 1 | 25 | PM | 10%
Phase 6 : Project Closure
Conduct final project | Conduct final project review | 6.1.1 | 5.1.1 , 5.1.2 | 2024-01-23 | 2024-01-23 | 1 |  | PM | 0%
| Archive project documents | 6.1.2 | 6.1.1 | 2024-01-23 | 2024-01-23 | 1 |  | PM | 0%
Handover project deliverables to the farm owner | meet the greenhouse owner and handover all documents | 6.2.1 | 6.1.1 , 4.2.1 , 4.2.2 , 4.2.3 , 4.2.4 , 4.2.5 | 2024-01-24 | 2024-01-24 | 1 |  | PM | 0%
Cost Table
|  | PV Cost |  |  |  | 713.3333
|  | Rainwater Harvesting System Cost |  |  |  | 9416.6667
|  | Total Cost |  |  |  | 10130
WBS Dictionary:
PM: Project Manager
SE: Strategic Engineer
ET: Electrical Technician
RHT: Rainwater Harvesting Technician
Note on B8: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on C8: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D8: Task Lead Enter the name of the Task Lead in this column.
Note on E8: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on F8: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G8: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H8: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on K8: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).

## AHP_1
Pair-wise Comparison Matrix | [9 empty] | Normalized Pair-wise Comparison Matrix
Factors | Cost Investment | Ease of Installation and Maintenance | Lifespan | Self-sufficiency | Sustainability with respect to SDGs | Integration with existing infrastructure | Regulatory compliance |  |  | Factors | Cost Investment | Ease of Installation and Maintenance | Lifespan | Self-sufficiency | Sustainability with respect to SDGs | Integration with existing infrastructure | Regulatory compliance | SUM | Criteria Weights | Criteria weight (%)
Cost Investment | 1 | 6 | 6 | 3 | 0.125 | 6 | 3 |  |  | Cost Investment | 0.098361 | 0.19355 | 0.36474 | 0.30928 | 0.063572 | 0.25 | 0.21053 | 1.49 | 0.21286 | 21.2861
Ease of Installation and Maintenance | 0.16667 | 1 | 0.2 | 0.2 | 0.11111 | 1 | 0.25 |  |  | Ease of Installation and Maintenance | 0.016393 | 0.032258 | 0.012158 | 0.020619 | 0.056509 | 0.041667 | 0.017544 | 0.19715 | 0.028164 | 2.8164
Lifespan | 0.16667 | 5 | 1 | 1 | 0.14286 | 4 | 1 |  |  | Lifespan | 0.016393 | 0.16129 | 0.06079 | 0.10309 | 0.072654 | 0.16667 | 0.070175 | 0.65106 | 0.093009 | 9.3009
Self-sufficiency | 0.33333 | 5 | 1 | 1 | 0.33333 | 2 | 1 |  |  | Self-sufficiency | 0.032787 | 0.16129 | 0.06079 | 0.10309 | 0.16953 | 0.083333 | 0.070175 | 0.68099 | 0.097285 | 9.7285
Sustainability with respect to SDGs | 8 | 9 | 7 | 3 | 1 | 9 | 7 |  |  | Sustainability with respect to SDGs | 0.78689 | 0.29032 | 0.42553 | 0.30928 | 0.50858 | 0.375 | 0.49123 | 3.1868 | 0.45526 | 45.526
Integration with existing infrastructure | 0.16667 | 1 | 0.25 | 0.5 | 0.11111 | 1 | 1 |  |  | Integration with existing infrastructure | 0.016393 | 0.032258 | 0.015198 | 0.051546 | 0.056509 | 0.041667 | 0.070175 | 0.28375 | 0.040535 | 4.0535
Regulatory compliance | 0.33333 | 4 | 1 | 1 | 0.14286 | 1 | 1 |  |  | Regulatory compliance | 0.032787 | 0.12903 | 0.06079 | 0.10309 | 0.072654 | 0.041667 | 0.070175 | 0.5102 | 0.072885 | 7.2885
Sum | 10.1667 | 31 | 16.45 | 9.7 | 1.9663 | 24 | 14.25 |  |  | Sum | [7 empty] | 7 | 1 | 100
Calculating Consistency | [10 empty] | Random Index values for different n criteria
[11 empty] | n | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Criteria Weights | 0.21286 | 0.028164 | 0.093009 | 0.097285 | 0.45526 | 0.040535 | 0.072885 |  |  |  | RI | 0 | 0 | 0.58 | 0.9 | 1.12 | 1.24 | 1.32 | 1.41 | 1.45
Factors | Cost Investment | Ease of Installation and Maintenance | Lifespan | Self-sufficiency | Sustainability with respect to SDGs | Integration with existing infrastructure | Regulatory compliance | Wieghted Sum Value | Ratio
Cost Investment | 0.21286 | 0.16898 | 0.55805 | 0.29185 | 0.056908 | 0.24321 | 0.21866 | 1.7505 | 8.2238
Ease of Installation and Maintenance | 0.035477 | 0.028164 | 0.018602 | 0.019457 | 0.050584 | 0.040535 | 0.018221 | 0.21104 | 7.4933
Lifespan | 0.035477 | 0.14082 | 0.093009 | 0.097285 | 0.065037 | 0.16214 | 0.072885 | 0.66665 | 7.1676
Self-sufficiency | 0.070954 | 0.14082 | 0.093009 | 0.097285 | 0.15175 | 0.08107 | 0.072885 | 0.70778 | 7.2753
Sustainability with respect to SDGs | 1.7029 | 0.25347 | 0.65106 | 0.29185 | 0.45526 | 0.36482 | 0.5102 | 4.2296 | 9.2904
Integration with existing infrastructure | 0.035477 | 0.028164 | 0.023252 | 0.048642 | 0.050584 | 0.040535 | 0.072885 | 0.29954 | 7.3896
Regulatory compliance | 0.070954 | 0.11266 | 0.093009 | 0.097285 | 0.065037 | 0.040535 | 0.072885 | 0.55236 | 7.5785
Sum | 2.1641 | 0.87308 | 1.53 | 0.94366 | 0.89516 | 0.97284 | 1.0386 | 8.4175 | 54.4186
[7 empty] | Maximum Eigenvalue (λmax) |  |  | 7.7741
[7 empty] | Consistency Index (CI) |  |  | 0.12901
[7 empty] | Consistency Ratio (CR) |  |  | 0.097737 | Consistent

## AHP_2
Criterion: Cost Investment | PV | Wind Turbine | Rainwater Harvesting System |  | Local Weights
PV | 1 | 5 | 9 | 15 | 0.66634
Wind Turbine | 0.2 | 1 | 5 | 6.2 | 0.27542
Rainwater Harvesting System | 0.11111 | 0.2 | 1 | 1.3111 | 0.058243
|  |  |  | 22.5111 | 1
Criterion: Ease of Installation and Maintenance | PV | Wind Turbine | Rainwater Harvesting System |  | Local Weights
PV | 1 | 7 | 9 | 17 | 0.64402
Wind Turbine | 0.14286 | 1 | 7 | 8.1429 | 0.30848
Rainwater Harvesting System | 0.11111 | 0.14286 | 1 | 1.254 | 0.047505
|  |  |  | 26.3968 | 1
Criterion: Lifespan | PV | Wind Turbine | Rainwater Harvesting System |  | Local Weights
PV | 1 | 0.16667 | 0.11111 | 1.2778 | 0.059126
Wind Turbine | 6 | 1 | 0.33333 | 7.3333 | 0.33933
Rainwater Harvesting System | 9 | 3 | 1 | 13 | 0.60154
|  |  |  | 21.6111 | 1
Criterion: Self-sufficiency | PV | Wind Turbine | Rainwater Harvesting System |  | Local Weights
PV | 1 | 0.33333 | 0.16667 | 1.5 | 0.094737
Wind Turbine | 3 | 1 | 0.33333 | 4.3333 | 0.27368
Rainwater Harvesting System | 6 | 3 | 1 | 10 | 0.63158
|  |  |  | 15.8333 | 1
Criterion: Sustainability with respect to SDGs | PV | Wind Turbine | Rainwater Harvesting System |  | Local Weights
PV | 1 | 5 | 2 | 8 | 0.57007
Wind Turbine | 0.2 | 1 | 0.33333 | 1.5333 | 0.10926
Rainwater Harvesting System | 0.5 | 3 | 1 | 4.5 | 0.32067
|  |  |  | 14.0333 | 1
Criterion: Integration with existing infrastructure | PV | Wind Turbine | Rainwater Harvesting System |  | Local Weights
PV | 1 | 7 | 7 | 15 | 0.75812
Wind Turbine | 0.14286 | 1 | 2 | 3.1429 | 0.15884
Rainwater Harvesting System | 0.14286 | 0.5 | 1 | 1.6429 | 0.083032
|  |  |  | 19.7857 | 1
Criterion: Regulatory Compliance | PV | Wind Turbine | Rainwater Harvesting System |  | Local Weights
PV | 1 | 7 | 0.33333 | 8.3333 | 0.36894
Wind Turbine | 0.14286 | 1 | 0.11111 | 1.254 | 0.055517
Rainwater Harvesting System | 3 | 9 | 1 | 13 | 0.57554
|  |  |  | 22.5873 | 1
Criteria
Alternatives | Cost Investment | Ease of Installation and Maintenance | Lifespan | Self-sufficiency | Sustainability with respect to SDGs | Integration with existing infrastructure | Difficulty of Regulatory Compliance
PV | 274 | Moderate | 20 | 318 | 50 | Moderate | Low
Wind Turbine | 1977 | Difficult | 25 | 601 | 46 | Moderate | High
Rainwater Harvesting System | 10000 | Moderate | 30 | 157 | 48 | Easy | Low
Sustainable Development Goals (SDGs) | PV | Wind Turbine | Rainwater Harvesting System
SDG 6: Clean Water and Sanitation | 0 | 0 | 10
SDG 7: Affordable and Clean Energy | 8 | 8 | 0
SDG 9: Industry, Innovation, and Infrastructure | 8 | 8 | 0
SDG 11: Sustainable Cities and Communities | 6 | 4 | 8
SDG 12: Responsible Consumption and Production | 6 | 6 | 8
SDG 13: Climate Action | 10 | 8 | 6
SDG 14: Life below Water | 6 | 6 | 8
SDG 15: Life on Land | 6 | 6 | 8
SUM | 50 | 46 | 48
Criteria
Criteria Weights | 0.21286 | 0.028164 | 0.093009 | 0.097285 | 0.45526 | 0.040535 | 0.072885
Alternatives | Cost Investment | Ease of Installation and Maintenance | Lifespan | Self-sufficiency | Sustainability with respect to SDGs | Integration with existing infrastructure | Regulatory Compliance | Composiste Weights | Rank
PV | 0.666 | 0.644 | 0.059 | 0.095 | 0.57 | 0.758 | 0.369 | 0.49175 | 1
Wind Turbine | 0.275 | 0.308 | 0.339 | 0.274 | 0.109 | 0.159 | 0.056 | 0.18555 | 3
Rainwater Harvesting System | 0.058 | 0.048 | 0.602 | 0.632 | 0.321 | 0.083 | 0.576 | 0.32266 | 2

## Decision Making Results
Alternatives | Cost Benefit Analysis (CBA) |  |  |  | Multi-Criteria Analysis (MCA)
| NPV | IRR | PP | BCR | AHP Ranks
PV | 3631.15 | 1.45 % | 0.3 years | 6.19 | 1
Wind Turbine | 1810.9 | 0.28 % | 1.8 years | 1.66 | 3
Rainwater Harvesting System | -7198.61 | -0.28 % | 15 years | 0.28 | 2
Alternatives | Cost Benefit Analysis (CBA)
| NPV | IRR | PP | BCR
Hybrid PV-Rainwater Harvesting System | 5178.85 | 0.23 % | 2,8 years | 1.5

## Sheet1
TASKS | WBS | PREDECESSOR | START | END | DAYS | Cost
Take Detailed Measurements of the Greenhouse Environment | 1.1.1 | Start | 2024-01-01 | 2024-01-01 | 1 | 10
Evaluate Suitable Space for Equipment Installation | 1.1.2 | 1.1.1 | 2024-01-01 | 2024-01-01 | 1 | 10
Assess water needs | 1.2.1 | 1.1.1 | 2024-01-02 | 2024-01-02 | 1 | 10
Analyze rainfall patterns | 1.2.2 | 1.1.1 | 2024-01-02 | 2024-01-02 | 1 | 10
Consider storage capacity | 1.2.3 | 1.2.1 , 1.2.2 | 2024-01-02 | 2024-01-02 | 1 | 10
Evaluate filtration requirements | 1.2.4 | 1.2.3 | 2024-01-02 | 2024-01-02 | 1 | 10
Design and specify components | 1.2.5 | 1.2.4 | 2024-01-02 | 2024-01-02 | 1 | 10
Calculate energy needs | 1.3.1 | 1.1.1 | 2024-01-03 | 2024-01-04 | 2 | 20
Evaluate solar radiation | 1.3.2 | 1.1.1 | 2024-01-03 | 2024-01-04 | 2 | 20
Determine panel size and quantity | 1.3.3 | 1.3.1 , 1.3.2 | 2024-01-03 | 2024-01-04 | 2 | 20
Design and specify components | 1.3.4 | 1.3.3 | 2024-01-03 | 2024-01-04 | 2 | 20
Integrate rainwater harvesting and PV systems | 1.4.1 | 1.2.5 , 1.3.4 | 2024-01-05 | 2024-01-05 | 1 | 10
Create detailed drawings and specifications | 1.4.2 | 1.4.1 | 2024-01-05 | 2024-01-05 | 1 | 10
Identify and select supplier for PV and its required components | 2.1.1 | 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 5
Identify and select suppliers for rainwater harvesting system components | 2.1.2 | 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 10
Purchase PV and required components | 2.2.1 | 2.1.1 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 310
Purchase Storage tanks | 2.2.2 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 3000
Purchase sediment filter | 2.2.3 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 800
Purchase ultraviolet (UV) filter | 2.2.4 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 1600
Purchase submersible pump | 2.2.5 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 800
Purchase control panel | 2.2.6 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 450
Purchase distribution pipes | 2.2.7 | 2.1.2 , 1.4.2 | 2024-01-08 | 2024-01-08 | 1 | 1000
Coordinate delivery schedules | 2.3.1 | 2.2.1 , 2.2.2 , 2.2.3 , 2.2.4 , 2.2.5 , 2.2.6 , 2.2.7 | 2024-01-08 | 2024-01-10 | 3 | 250
Clearing and grading the ground for tank placement | 3.1.1 | 2.2.2 | 2024-01-09 | 2024-01-09 | 1 | 800
Excavation for tank installation | 3.1.2 | 2.2.2 | 2024-01-10 | 2024-01-10 | 1 | 1600
Delivery and installation of rainwater storage tanks | 3.2.1 | 2.3.1 | 2024-01-11 | 2024-01-11 | 1 | 40
Connection of pipes to the tank | 3.2.2 | 2.3.1 , 3.2.1 | 2024-01-12 | 2024-01-12 | 1 | 160
Installation of sediment filter | 3.3.1 | 3.2.1 , 2.3.1 | 2024-01-15 | 2024-01-15 | 1 | 250
Installation of ultraviolet (UV) filter | 3.3.2 | 3.2.1 , 2.3.1 | 2024-01-15 | 2024-01-15 | 1 | 300
Installation of submersible pump | 3.4.1 | 3.2.1 , 2.3.1 | 2024-01-16 | 2024-01-16 | 1 | 200
Installation of control panel | 3.4.2 | 3.4.1 , 2.3.1 | 2024-01-16 | 2024-01-16 | 1 | 120
Installation of collection and distribution pipes | 3.5.1 | 3.4.1 , 2.3.1 | 2024-01-17 | 2024-01-17 | 1 | 600
Installation of irrigation system | 3.5.2 | 3.4.1 , 2.3.1 | 2024-01-17 | 2024-01-17 | 1 | 600
Install PV modules and mounting structures | 3.6.1 | 2.3.1 | 2024-01-11 | 2024-01-11 | 1 | 100
Connect PV system to electrical infrastructure | 3.6.2 | 3.6.1 | 2024-01-12 | 2024-01-12 | 1 | 80
Perform functionality tests on rainwater harvesting system and optimize it | 4.1.1 | 3.5.2 | 2024-01-18 | 2024-01-18 | 1 | 20
Perform electrical tests on the PV system and optimize it | 4.1.2 | 3.6.2 | 2024-01-18 | 2024-01-18 | 1 | 20
Register for the Conto Termico 2.0 (CT2) program | 4.2.1 | 2.2.1 | 2024-01-09 | 2024-01-18 | 10 | 100
Obtain electrical and structural permits | 4.2.2 | 2.2.1 | 2024-01-09 | 2024-01-22 | 14 | 100
Obtain certifications for PV components | 4.2.3 | 2.2.1 | 2024-01-09 | 2024-01-16 | 8 | 100
Obtain certifications for rainwater harvesting system components | 4.2.4 | 1.4.2 | 2024-01-09 | 2024-01-12 | 4 | 100
Obtain authorization for rainwater discharge | 4.2.5 | 1.4.2 | 2024-01-09 | 2024-01-23 | 15 | 100
Create user manuals for rainwater harvesting system | 5.1.1 | 4.1.1 | 2024-01-19 | 2024-01-19 | 1 | 200
Create user manuals for PV system | 5.1.2 | 4.1.2 | 2024-01-22 | 2024-01-22 | 1 | 50
Conduct final project review | 6.1.1 | 5.1.1 , 5.1.2 | 2024-01-23 | 2024-01-23 | 1
Archive project documents | 6.1.2 | 6.1.1 | 2024-01-23 | 2024-01-23 | 1
meet the greenhouse owner and handover all documents | 6.2.1 | 6.1.1 , 4.2.1 , 4.2.2 , 4.2.3 , 4.2.4 , 4.2.5 | 2024-01-24 | 2024-01-24 | 1
Formulas:
END = IF(ISBLANK([START])," - ",IF([DAYS]=0,[START],[START]+[DAYS]-1))
Note on A1: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B1: Task Lead Enter the name of the Task Lead in this column.
Note on C1: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on D1: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on E1: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on F1: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.